## GanttChart
Gantt Chart					© 2008 Vertex42 LLC	0
				Download Professional Version for Excel
cycling-adventures.org
Stessaonda

	Projektleiter:	Lukas
	Today's Date:	11/15/2015	(So)	(vertical red line)
[42]	Startdatum:	11/1/2015	(So)					Wochenstart (Sonntag=1):	2	11/2/2015	11/3/2015	11/4/2015	11/5/2015	11/6/2015	11/7/2015	11/8/2015	11/9/2015	11/10/2015	11/11/2015	11/12/2015	11/13/2015	11/14/2015	11/15/2015	11/16/2015	11/17/2015	11/18/2015	11/19/2015	11/20/2015	11/21/2015	11/22/2015	11/23/2015	11/24/2015	11/25/2015	11/26/2015	11/27/2015	11/28/2015	11/29/2015	11/30/2015	12/1/2015	12/2/2015	12/3/2015	12/4/2015	12/5/2015	12/6/2015	12/7/2015	12/8/2015	12/9/2015	12/10/2015	12/11/2015	12/12/2015	12/13/2015	12/14/2015	12/15/2015	12/16/2015	12/17/2015	12/18/2015	12/19/2015	12/20/2015	12/21/2015	12/22/2015	12/23/2015	12/24/2015	12/25/2015	12/26/2015	12/27/2015	12/28/2015	12/29/2015	12/30/2015	12/31/2015	1/1/2016	1/2/2016	1/3/2016	1/4/2016	1/5/2016	1/6/2016	1/7/2016	1/8/2016	1/9/2016	1/10/2016	1/11/2016	1/12/2016	1/13/2016	1/14/2016	1/15/2016	1/16/2016	1/17/2016	1/18/2016	1/19/2016	1/20/2016	1/21/2016	1/22/2016	1/23/2016	1/24/2016	1/25/2016	1/26/2016	1/27/2016	1/28/2016	1/29/2016	1/30/2016	1/31/2016	2/1/2016	2/2/2016	2/3/2016	2/4/2016	2/5/2016	2/6/2016	2/7/2016	2/8/2016	2/9/2016	2/10/2016	2/11/2016	2/12/2016	2/13/2016	2/14/2016	2/15/2016	2/16/2016	2/17/2016	2/18/2016	2/19/2016	2/20/2016	2/21/2016	2/22/2016	2/23/2016	2/24/2016	2/25/2016	2/26/2016	2/27/2016	2/28/2016	2/29/2016	3/1/2016	3/2/2016	3/3/2016	3/4/2016	3/5/2016	3/6/2016	3/7/2016	3/8/2016	3/9/2016	3/10/2016	3/11/2016	3/12/2016	3/13/2016	3/14/2016	3/15/2016	3/16/2016	3/17/2016	3/18/2016	3/19/2016	3/20/2016	3/21/2016	3/22/2016	3/23/2016	3/24/2016	3/25/2016	3/26/2016	3/27/2016	3/28/2016	3/29/2016	3/30/2016	3/31/2016	4/1/2016	4/2/2016	4/3/2016	4/4/2016	4/5/2016	4/6/2016	4/7/2016	4/8/2016	4/9/2016	4/10/2016	4/11/2016	4/12/2016	4/13/2016	4/14/2016	4/15/2016	4/16/2016	4/17/2016	4/18/2016	4/19/2016	4/20/2016	4/21/2016	4/22/2016	4/23/2016	4/24/2016	4/25/2016	4/26/2016	4/27/2016	4/28/2016	4/29/2016	4/30/2016	5/1/2016	5/2/2016	5/3/2016	5/4/2016	5/5/2016	5/6/2016	5/7/2016	5/8/2016	5/9/2016	5/10/2016	5/11/2016	5/12/2016	5/13/2016	5/14/2016	5/15/2016	5/16/2016	5/17/2016	5/18/2016	5/19/2016	5/20/2016	5/21/2016	5/22/2016	5/23/2016	5/24/2016	5/25/2016	5/26/2016	5/27/2016	5/28/2016	5/29/2016	5/30/2016	5/31/2016	6/1/2016	6/2/2016	6/3/2016	6/4/2016	6/5/2016	6/6/2016	6/7/2016	6/8/2016	6/9/2016	6/10/2016	6/11/2016	6/12/2016	6/13/2016	6/14/2016	6/15/2016	6/16/2016	6/17/2016	6/18/2016	6/19/2016	6/20/2016	6/21/2016	6/22/2016	6/23/2016	6/24/2016	6/25/2016	6/26/2016
WBS	Aufgabe	Zuständig	Start	Ende	Dauer (Tage)	% fertig	Arbeitstage	Tage erledigt	Tage verbleibend		02 - Nov - 15					09 - Nov - 15					16 - Nov - 15					23 - Nov - 15					30 - Nov - 15					07 - Dez - 15					14 - Dez - 15					21 - Dez - 15					28 - Dez - 15					04 - Jan - 16					11 - Jan - 16					18 - Jan - 16					25 - Jan - 16					01 - Feb - 16					08 - Feb - 16					15 - Feb - 16					22 - Feb - 16					29 - Feb - 16					07 - Mrz - 16					14 - Mrz - 16					21 - Mrz - 16					28 - Mrz - 16					04 - Apr - 16					11 - Apr - 16					18 - Apr - 16					25 - Apr - 16					02 - Mai - 16					09 - Mai - 16					16 - Mai - 16					23 - Mai - 16					30 - Mai - 16					06 - Jun - 16					13 - Jun - 16					20 - Jun - 16

1	Website	Lukas	2.11.15	16.11.16	380	4%	273	16	364
1.1	Hosting	Lukas	4.01.16	5.01.16	1	0%	2	0	1
1.2	Installation CMS lokal	Lukas	21.11.15	28.11.15	7	100%	5	7	0
1.30	Installation CMS auf Server	Lukas	11.01.16	18.01.16	7	0%	6	0	7
1.4	Definition Anmeldeformular	alle	4.12.15	7.12.15	3	0%	2	0	3
1.5	Wireframes	alle	2.11.15	1.01.16	60	0%	45	0	60
1.5.1	Wireframe Startseite	alle	2.11.15	1.01.16	60	0%	45	0	60
1.5.2	Wireframe Inhaltsseite	alle	2.11.15	1.01.16	60	0%	45	0	60
1.5.3	Wireframe Reiseseite	alle	2.11.15	1.01.16	60	0%	45	0	60
1.5.4	Wireframe Anmeldeformular	alle	2.11.15	1.01.16	60	33%	45	19	41
1.5.4	Datenmodellierung	alle	7.12.15	14.12.15	7	0%	6	0	7
1.6	Tests Anmeldeformular	Roli/Lutz	8.02.16	15.02.16	7	0%	6	0	7
1.7	Schnittstelle Anmeldefomular <> Billomat	Lukas	15.02.16	17.03.16	31	0%	24	0	31
1.8	Tests Anmeldeformular & Billomat	Roli/Lutz	17.03.16	24.03.16	7	0%	6	0	7
1.9	Korrekturen Anmeldeformular & Billomat	Lukas	24.03.16	31.03.16	7	0%	6	0	7
1.10	Layout	Ruth	1.03.16	20.04.16	50	0%	37	0	50
1.11	Inhaltserstellung für jede Reise	Orgas	2.05.16	1.06.16	30	0%	23	0	30
1.12	Inhalte abfüllen für jede Reise	Ruth	1.06.16	16.07.16	45	0%	33	0	45
1.13	FAQ Inhalte erstellen	Lutz/Roli	1.05.16	9.08.16	100	0%	72	0	100
1.20	Abschlusstests	alle	19.08.16	26.08.16	7	0%	6	0	7
1.30	Aufschaltung Website v. 1.0	alle	30.08.16	31.08.16	1	0%	2	0	1
1.40	Blog für Reisen	Lukas	1.11.16	16.11.16	15	0%	12	0	15
2	Landingpages	Ruth	21.11.15	15.08.16	268	0%	191	0	268
2.1	Wireframe	L/R/L	21.11.15	21.12.15	30	0%	21	0	30
2.2	Basislayout erstellen	Ruth	1.03.16	20.04.16	50	0%	37	0	50
2.3	Inhaltserstellung für jede Reise	Orgas	2.05.16	1.06.16	30	0%	23	0	30
2.4	Landingpages erstellen für jede Reise	Ruth	1.06.16	16.07.16	45	0%	33	0	45
2.5	SEO Optimierungen	Ruth/Lukas	8.08.16	15.08.16	7	0%	6	0	7
3	Billomat	Lukas	25.04.16	3.09.16	131	0%	95	0	131
3.1	Kundenverwaltung	Lukas	1.03.16	18.03.16	17	0%	14	0	17
3.2	Dokumentvorlagen	Lukas	1.03.16	8.03.16	7	0%	6	0	7
3.3	Artikelverwaltung	Lukas	12.05.16	29.05.16	17	0%	12	0	17
3.3	Loginbereich	Lukas	29.05.16	5.07.16	37	0%	27	0	37
3.4	Dokumentation	Lukas	5.08.16	3.09.16	29	0%	21	0	29
4	SEO	alle	1.02.16	16.02.16	15	0%	12	0	15
4.1	Keywords definieren	alle	1.02.16	16.02.16	15	0%	12	0	15
5	Analytics	Lukas/Ruth	1.07.16	3.09.16	64	0%	46	0	64
5.1	Google Analytics & Adwords registrieren	Lukas	1.07.16	3.07.16	2	0%	1	0	2
5.2	Analytics Conversions definieren	Lukas/Ruth	8.07.16	10.07.16	2	0%	1	0	2
5.3	Analytics Reporting definieren	Lukas/Ruth	8.07.16	15.07.16	7	0%	6	0	7
5.4	Allgemeine Kampagne vorbereiten	Ruth	1.09.16	3.09.16	2	0%	2	0	2
6	Wordpress	Lukas	1.10.16	10.10.16	9	0%	6	0	9
6.1	Installation CMS	Lukas	1.10.16	3.10.16	2	0%	1	0	2
6.2	Templateanpassungen	Lukas	3.10.16	10.10.16	7	0%	6	0	7
7	Online-Umfrage	Lutz/Roli	1.11.16	22.12.16	51	0%	38	0	51
7.1	Evaluation Tool	Lutz/Roli	1.11.16	8.11.16	7	0%	6	0	7
7.2	Fragen definieren	alle	15.11.16	22.11.16	7	0%	6	0	7
7.3	Fragebogen umsetzen	Lutz	1.12.16	22.12.16	21	0%	16	0	21

HELP / - Modify the GREEN cells and the WBS, Tasks, and Task Lead columns. The rest of the columns are formulas. / - The number of weeks shown in the gantt chart is limited by the maximum number of columns available. / - The Start Date that you choose determines the first week in the gantt chart, starting on a Monday. / - Change the first day of the week via cell K8 / - Use the slider to adjust the range of dates shown in the gantt chart. / - Only 34 weeks can be shown/printed at one time, because each week uses up 7 columns. / Q: How do I make Task 2 start the day after the end of Task 1? / Use the following formula for the start date of Task 2: / =EndDate+1 / where EndDate is the reference to the cell containing the end date of task 1 / Q: How do I add/insert tasks and subtasks? / Copy the entire ROW (or a group of rows) for the type of task(s) you want to add and then right-click on the row where you want to insert the new tasks, then select Insert Copied Cells. / Important Note: When inserting a new subtask after the last subtask or before the first subtask, you will need to update the formulas for calculating the Level 1 %Complete and Duration (see below) to include the new subtask, because the ranges won't automatically expand to include the additional row. / Q: How do I calculate the %Complete for a Level 1 task based upon the %Complete of all of the associated subtasks? / Example: If Task 1 is on row 11 and the subtasks are on rows 12-15, use the following formula: / =SUMPRODUCT(F12:F15;G12:G15)/SUM(F12:F15) / Q: How do I calculate the Duration for a Level 1 task based upon the largest end date of a sub task? / Example: If the Level 1 task is on row 11 and the sub tasks are on rows 12-15, use the following formula / =MAX(E12:E15)-D11 / Q: How can I include holidays in the calculation of the Working Days? / You can add a list of holidays to exclude in the NETWORKDAYS function. See the help on that function. / Q: How do I change the print settings? / Select the entire range of cells that you want to print and then define a Print Range in the Format menu. Then go to Format > Page and select the Sheet tab. Adjust the Scaling mode as desired.